## Regular Work
Quantity/ Pay Item Tracking System
Period Summary Report
Project: MCP- 0XX
|  |  | Description: Big Micro Contract Project | [5 empty] | Estimate No.: | 3
|  |  | Contractor: Micro Contract R Us | [5 empty] | Period: | 9/17/03 to 10/16/03
TOTAL
Pay Item |  | Plan | Description |  |  |  | This | Total To |  |  |  | % | QUANTITY | PREVIOUS | TOTAL | THIS | CONTRACT |  |  |  | EARNED THIS
No. |  | Item |  | Unit | Plan | Previous | Estimate | Date | Unit Price | $ This Est | $ To-Date | Complete | TO DATE | PAID | TO DATE | ESTIMATE | VALUE | Bid |  |  | ESTIMATE
1 | 10 | Plan | Item 1 | MO | 12 | 2 | 1 | 3 | 4321 | 4321 | 12963 | 25% | 3 | 8642 | 12963 | 4321 | 51852 | 7008 | 44844
2 |  |  | Item 2 | LS | 1 | 0.5717 | 0.01805 | 0.58975 | 7908.4 | 142.75 | 4663.9789 | 58.98%
3 |  |  | Item 2 | EA | 187 | 117 | 25 | 142 | 54.81 | 1370.25 | 7783.02 | 75.94%
[17 empty] | 51852 | 7008 | 44844 | 0
TOTAL | [9 empty] | 5834 | 25409.9989 | 49% |  | 8642 | 12963 | 4321
[15 empty] | 4321 |  | 6523965 | -491581
[17 empty] | 12582% | -439729
8642
[17 empty] | 6523965 | 5955
[14 empty] | 162803.61 |  |  | 77.62%
[14 empty] | -8460441.02 |  |  | 4471948
0.50268

## SA's
Quantity/ Pay Item Tracking System
Period Summary Report
Project: PROJECT 111
| Description: 111- S.A. Work | [7 empty] | Estimate No.: | 25
| Contractor: Contractor's Name | [7 empty] | Period: | 4/26/03 to 5/25/03
Pay Item | Plan Quantity |  | Desription |  | SA |  | This | Total To |  |  |  | %
No. | Item | CPR # |  | Unit | Quantity | Previous | Estimate | Date | Unit Price | $ This Est | $ To-Date | Complete
03-1614-140-707RA | RECLAIM CONFLICTS 4" | 3 |  | EA | 6 | 6 | 0 | 6 | 837.28 | 0 | 5023.68 | 100%
03-1614-140-720RA | RECLAIM CONFLICTS 8" | 3 |  | EA | 18 | 18 | 0 | 18 | 850.44 | 0 | 15307.92 | 100%
03-1610-142-07R | RECLAIM FITTING (F&I)(DIP)(Elbows-45/90)(4") | 3 |  | EA | 24 | 24 | 0 | 24 | 90 | 0 | 2160 | 100%
03-1692-213R | RECLAIM PIPE RESTRAINT 4" | 3 |  | EA | 20 | 20 | 0 | 20 | 60.17 | 0 | 1203.4 | 100%
03-1692-218R | RECLAIM PIPE RESTRAINT 8" | 3 |  | EA | 20 | 20 | 0 | 20 | 73.33 | 0 | 1466.6 | 100%
04-550-76-142 | Gate at Lift Station (F&I) | 19 |  | LS | 1 | 0 | 1 | 1 | 552.67 | 552.67 | 552.67 | 100%
06-1614-140-724 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (16") | N/A | LF | LF | 4 | 0 | 4 | 4 | 35 | 140 | 140 | 100%
06-1614-140-720 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (10") | N/A | LF | LF | 2 | 0 | 2 | 2 | 21 | 42 | 42 | 100%
06-1614-140-709 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (8") | N/A | LF | LF | 3 | 0 | 3 | 3 | 19 | 57 | 57 | 100%
06-1614-140-707R | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (4") | N/A | LF | LF | 9 | 0 | 9 | 9 | 13.75 | 123.75 | 123.75 | 100%
06-1642-156-09R | WATER VALVE (F & I) (DI) (GATE) (8") | N/A | EA | EA | 1 | 0 | 1 | 1 | 875 | 875 | 875 | 100%
06-1642-156-07R | WATER VALVE (F & I) (DI) (GATE) (4") | N/A | EA | EA | 1 | 0 | 1 | 1 | 550 | 550 | 550 | 100%
06-1642-156-05R | WATER VALVE (F & I) (DI) (GATE) (2") | N/A | EA | EA | 1 | 0 | 1 | 1 | 400 | 400 | 400 | 100%
06-1611-140-206R | 8" X 45 DEGREE BEND | N/A | EA | EA | 43 | 0 | 43 | 43 | 170 | 7310 | 7310 | 100%
06-1513-160-321S | 12" PVC SEWER PIPE 14'-16' DEPTH | N/A | LF | LF | 18 | 0 | 18 | 18 | 41 | 738 | 738 | 100%
06-1513-160-311S | 18" PVC SEWER PIPE 16'-18' DEPTH | N/A | LF | LF | 167 | 0 | 167 | 167 | 44 | 7348 | 7348 | 100%
06-1541-111-13S | UTILITY MANHOLE (>12') | N/A | EA | EA | 3 | 0 | 3 | 3 | 4600 | 13800 | 13800 | 100%
06-1512-160-121S | 12" PVC FORCE MAIN | N/A | LF | LF | 57 | 0 | 57 | 57 | 17 | 969 | 969 | 100%
06-1610-142-14 | WATER FITTING (F & I) (DIP[) (ELBOW-45/90) (12") | N/A | EA | EA | -2 | 0 | -2 | -2 | 300 | -600 | -600 | 100%
06-1610-147-09 | WATER FITTING (F & I) ( DIP) (PLUGS) (8") | N/A | EA | EA | -2 | 0 | -2 | -2 | 75 | -150 | -150 | 100%
06-1610-147-10 | WATER FITTING (F & I) ( DIP) (PLUGS) (10") | N/A | EA | EA | -1 | 0 | -1 | -1 | 85 | -85 | -85 | 100%
06-1610-147-11 | WATER FITTING (F & I) ( DIP) (PLUGS) (12") | N/A | EA | EA | -1 | 0 | -1 | -1 | 110 | -110 | -110 | 100%
06-1610-147-13 | WATER FITTING (F & I) ( DIP) (PLUGS) (16") | N/A | EA | EA | -2 | 0 | -2 | -2 | 250 | -500 | -500 | 100%
06-1613-130-502 | WATER PIPE (PUSH-ON JT) (F & I) (PVC CL200) (1") | N/A | LF | LF | -161 | 0 | -161 | -161 | 3 | -483 | -483 | 100%
06-1613-130-505 | WATER PIPE (PUSH-ON JT) (F & I) (PVC CL200) (2") | N/A | LF | LF | -45 | 0 | -45 | -45 | 4.25 | -191.25 | -191.25 | 100%
06-1614-140-721 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (12") | N/A | LF | LF | -18 | 0 | -18 | -18 | 21 | -378 | -378 | 100%
06-1635-141-402 | 12"X1" TAPPING SLEEVE | N/A | EA | EA | -1 | 0 | -1 | -1 | 550 | -550 | -550 | 100%
06-1642-156-05 | WATER VALVE (F & I) (DI) (GATE) (2") | N/A | EA | EA | -1 | 0 | -1 | -1 | 400 | -400 | -400 | 100%
06-1614-140-720R | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (8") | N/A | LF | LF | -147 | 0 | -147 | -147 | 14 | -2058 | -2058 | 100%
06-1612-130-105R | RECLAIMED WATER PIPE (SOLVENT JT) (F & I) (PVC CL80) (2") | N/A | LF | LF | -77 | 0 | -77 | -77 | 7 | -539 | -539 | 100%
06-1611-140-400R | 4" X 2" REDUCER | N/A | EA | EA | -1 | 0 | -1 | -1 | 70 | -70 | -70 | 100%
06-1611-140-300R | 8" X 2" TEE | N/A | EA | EA | -1 | 0 | -1 | -1 | 180 | -180 | -180 | 100%
06-1611-140-707R | 4" PLUG | N/A | EA | EA | -12 | 0 | -12 | -12 | 75 | -900 | -900 | 100%
06-1611-140-709R | 8" PLUG | N/A | EA | EA | -6 | 0 | -6 | -6 | 76 | -456 | -456 | 100%
06-1648-100-2R | TIE TO EXISTING LINE | N/A | EA | EA | -2 | 0 | -2 | -2 | 1200 | -2400 | -2400 | 100%
06-1541-111-12S | UTILITY MANHOLE (6' - 12') | N/A | EA | EA | -3 | 0 | -3 | -3 | 3000 | -9000 | -9000 | 100%
06-1610-142-8S | 12" WYE | N/A | EA | EA | -1 | 0 | -1 | -1 | 1100 | -1100 | -1100 | 100%
06-455-133 | SHEET PILING (30' DEEP X 50' LONG) | N/A | SF | SF | -1500 | 0 | -1500 | -1500 | 10 | -15000 | -15000 | 100%
TOTAL | [9 empty] | -2244.83 | 22916.77
SAMPLE

## Extra Work
Quantity/ Pay Item Tracking System
Period Summary Report
Project: PROJECT 111
| Description: 111- Extra Work | [7 empty] | Estimate No.: | 25
| Contractor: Contractor's Name | [7 empty] | Period: | 4/26/03 to 5/25/03
Pay Item | Plan Quantity |  | Desription |  | SA |  | This | Total To |  |  |  | %
No. | Item | CPR # |  | Unit | Quantity | Previous | Estimate | Date | Unit Price | $ This Est | $ To-Date | Complete
06-1614-140-724 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (16") | N/A | LF | LF | 4 | 4 | -4 | 0 | 35 | -140 | 0 | 0%
06-1614-140-720 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (10") | N/A | LF | LF | 2 | 2 | -2 | 0 | 21 | -42 | 0 | 0%
06-1614-140-709 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (8") | N/A | LF | LF | 3 | 3 | -3 | 0 | 19 | -57 | 0 | 0%
06-1614-140-707R | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (4") | N/A | LF | LF | 9 | 9 | -9 | 0 | 13.75 | -123.75 | 0 | 0%
06-1642-156-09R | WATER VALVE (F & I) (DI) (GATE) (8") | N/A | EA | EA | 1 | 1 | -1 | 0 | 875 | -875 | 0 | 0%
06-1642-156-07R | WATER VALVE (F & I) (DI) (GATE) (4") | N/A | EA | EA | 1 | 1 | -1 | 0 | 550 | -550 | 0 | 0%
06-1642-156-05R | WATER VALVE (F & I) (DI) (GATE) (2") | N/A | EA | EA | 1 | 1 | -1 | 0 | 400 | -400 | 0 | 0%
06-1611-140-206R | 8" X 45 DEGREE BEND | N/A | EA | EA | 43 | 43 | -43 | 0 | 170 | -7310 | 0 | 0%
06-1513-160-321S | 12" PVC SEWER PIPE 14'-16' DEPTH | N/A | LF | LF | 18 | 18 | -18 | 0 | 41 | -738 | 0 | 0%
06-1513-160-311S | 18" PVC SEWER PIPE 16'-18' DEPTH | N/A | LF | LF | 167 | 167 | -167 | 0 | 44 | -7348 | 0 | 0%
06-1541-111-13S | UTILITY MANHOLE (>12') | N/A | EA | EA | 3 | 3 | -3 | 0 | 4600 | -13800 | 0 | 0%
06-1512-160-121S | 12" PVC FORCE MAIN | N/A | LF | LF | 57 | 57 | -57 | 0 | 17 | -969 | 0 | 0%
06-1610-142-14 | WATER FITTING (F & I) (DIP[) (ELBOW-45/90) (12") | N/A | EA | EA | -2 | -2 | 2 | 0 | 300 | 600 | 0 | 0%
06-1610-147-09 | WATER FITTING (F & I) ( DIP) (PLUGS) (8") | N/A | EA | EA | -2 | -2 | 2 | 0 | 75 | 150 | 0 | 0%
06-1610-147-10 | WATER FITTING (F & I) ( DIP) (PLUGS) (10") | N/A | EA | EA | -1 | -1 | 1 | 0 | 85 | 85 | 0 | 0%
06-1610-147-11 | WATER FITTING (F & I) ( DIP) (PLUGS) (12") | N/A | EA | EA | -1 | -1 | 1 | 0 | 110 | 110 | 0 | 0%
06-1610-147-13 | WATER FITTING (F & I) ( DIP) (PLUGS) (16") | N/A | EA | EA | -2 | -2 | 2 | 0 | 250 | 500 | 0 | 0%
06-1613-130-502 | WATER PIPE (PUSH-ON JT) (F & I) (PVC CL200) (1") | N/A | LF | LF | -161 | -161 | 161 | 0 | 3 | 483 | 0 | 0%
06-1613-130-505 | WATER PIPE (PUSH-ON JT) (F & I) (PVC CL200) (2") | N/A | LF | LF | -45 | -45 | 45 | 0 | 4.25 | 191.25 | 0 | 0%
06-1614-140-721 | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (12") | N/A | LF | LF | -18 | -18 | 18 | 0 | 21 | 378 | 0 | 0%
06-1635-141-402 | 12"X1" TAPPING SLEEVE | N/A | EA | EA | -1 | -1 | 1 | 0 | 550 | 550 | 0 | 0%
06-1642-156-05 | WATER VALVE (F & I) (DI) (GATE) (2") | N/A | EA | EA | -1 | -1 | 1 | 0 | 400 | 400 | 0 | 0%
06-1614-140-720R | WATER PIPE (MECH. JT) (F & I) (DIP CL50) (8") | N/A | LF | LF | -147 | -147 | 147 | 0 | 14 | 2058 | 0 | 0%
06-1612-130-105R | RECLAIMED WATER PIPE (SOLVENT JT) (F & I) (PVC CL80) (2") | N/A | LF | LF | -77 | -77 | 77 | 0 | 7 | 539 | 0 | 0%
06-1611-140-400R | 4" X 2" REDUCER | N/A | EA | EA | -1 | -1 | 1 | 0 | 70 | 70 | 0 | 0%
06-1611-140-300R | 8" X 2" TEE | N/A | EA | EA | -1 | -1 | 1 | 0 | 180 | 180 | 0 | 0%
06-1611-140-707R | 4" PLUG | N/A | EA | EA | -12 | -12 | 12 | 0 | 75 | 900 | 0 | 0%
06-1611-140-709R | 8" PLUG | N/A | EA | EA | -6 | -6 | 6 | 0 | 76 | 456 | 0 | 0%
06-1648-100-2R | TIE TO EXISTING LINE | N/A | EA | EA | -2 | -2 | 2 | 0 | 1200 | 2400 | 0 | 0%
06-1541-111-12S | UTILITY MANHOLE (6' - 12') | N/A | EA | EA | -3 | -3 | 3 | 0 | 3000 | 9000 | 0 | 0%
06-1610-142-8S | 12" WYE | N/A | EA | EA | -1 | -1 | 1 | 0 | 1100 | 1100 | 0 | 0%
06-455-133 | SHEET PILING (30' DEEP X 50' LONG) | N/A | SF | SF | -1500 | -1500 | 1500 | 0 | 10 | 15000 | 0 | 0%
TOTAL | [9 empty] | 2797.5 | 0